## Foglio1
Fashion Emotion Lexicon (FEL) — Visiting Research Schedule
Period (2 Weeks) | FEL Phase | Main Focus / Tasks | HITL Validation | Expected Deliverables
Jan 19–31, 2026 | Orientation & Review (Kickoff) | • Arrival & setup at USI. • Present FEL draft and progress. | — | Confirmed plan.
Feb 1–15, 2026 | D6 – Ontology Refinement | • Refine ontology logic. | — | FEL Ontology.
Feb 16–29, 2026 | D6–D7 – Ontology Finalization & IR Alignment | • Verify consistency. • Map ontology attributes to IR vocabulary. • Design emotion–style relations for retrieval. • Finalize Lexicon v1.0. | Mini external pilot review — domain experts check clarity and usability of aesthetic/emotional terms before full IR integration. | Ontology v1.0 (ready for IR) + Reviewed Lexicon prototype.
Mar 1–15, 2026 | D7 – IR Integration | • Implement hybrid IR. • Add emotion-aware re-ranking using ontology signals. | — | Emotion-aware IR prototype.
Mar 16–31, 2026 | D8 – Evaluation & Feedback Loop | • Test retrieval performance. • Analyze ontology–retrieval synergy. • Iterate improvements. | — | Integrated Ontology–IR prototype.
Apr 1–15, 2026 | D9 – Multilingual & Cultural Validation | • Align EN–IT–KR lexicons. • Validate emotional mappings. | Experts: fashion researchers (EN–IT–KR(if possible)). General users: emotional resonance survey (“Does ‘minimal’ evoke calmness?”). | Cross-Cultural FEL v1.0.
Apr 16–19, 2026 | D10 – Wrap-up & Reporting | • Summarize all outputs. • Finalize documentation. • Conduct final review. | — | FEL Package (Ontology + IR + Validation).